## Stakeholders
SGSEAM Stakeholders
SGSEAM Stakeholder | BuildingOS Users | Tasks
Player | Building resident | Use BuildingDashboard to view and participate.
System admin | Internal system admin or developer | Install software, backup, patch, monitor and scale the system.
Game designer | Behavior Change Manager, Technical Manager, Competition Director, Research Manager | • Decide on a competition format/structure • Set up buildings, meters, and competition in BuildingOS
Game manager | Technical Manager, Marketing Manager, Building Captain Manager, Events Manager | • Collect, verify baseline and competition data, enter into BuildingOS • Kick-off and other events • Coordinate competition prizes • Manage social media • Monitor competition status
Game developer | Internal or external Developer | • Develop interface to support other meters • Customize dashboard interface
CCN COT Role Mapped to SGSEAM Stakeholder
CCN COT Role |  | SGSEAM Stakeholder
Competition Director (CD) |  | Game Designer
Technical Manager |  | Game Designer, Game Manager
Marketing Manager (MM) |  | Game Manager
Building Captain Manager (BCaM) |  | Game Manager
Behavior Change Manager (BChM) |  | Game Designer
Events Manager (EM) |  | Game Manager
Research Manager (RM) |  | Game Designer

## Approach
SGSEAM Assessment Approach
Stakeholder | Assessment Approaches | Expected Outcomes
Player | Pre-post effectiveness study | Determine effectiveness in resource usage reduction.
| Usability survey | identify problem areas in game interface
| Engagement metrics | determine the extent of engagement
System admin | Post-hoc admin interview | identify strengths and weaknesses in the installation and maintenance process.
Game designer | Post-hoc designer interview | Determine strengths and weaknesses in the game design interface.
Game manager | Post-hoc manager interview | Determine strengths and weaknesses in the game managing interface.
Game developer | Post-hoc developer interview | Determine strengths and weaknesses in developing enhancement.

## Participants
Participants Chosen for SGSEAM Assessment
Stakeholder | Person name | Orgainization | Contact
Player
System admin
Game designer
Game manager
Game developer

## Schedule
SGSEAM Assessment Schedule
Week | CCN Milestone | CCN Task | SGSEAM Task
Feb 3 - 7 | CCN window starts
Feb 10 - 14 |  | Set up buildings, meters, and competition in BuildingOS | Finalize stakeholders and assessment approaches
Feb 17 - 21 |  |  | Choose participants
Feb 24 - 28 |  | Data collection dry run week, troubleshooting and resolve problems | Game developer Development using Lucid APIs
Mar 3 - 7 |  |  | Finalize interview and survey questionnaires
Mar 10 - 14 | Baseline | Collect & verify baseline data | Game developer post-hoc interview
Mar 17 - 21 |  |  | System admin post-hoc interview
Mar 24 - 28 | Competition | Verify baseline data, Collect and verify competition data, Enter data into BuildingOS; Kick-off and other events; Social media
Mar 31 - Apr 4
Apr 7 - 11
Apr 14 - 18 |  | Collect, verify and enter final competition data into BuildingOS | Game designer post-hoc interview; Obtain log data
Apr 21 - 25 |  |  | Player effectiveness study
Apr 28 - May 2 |  |  | Player usability survey
May 5 - 9 |  |  | Game manager post-hoc interview
May 12 - 16 |  |  | Analyze the data; Interpret strength and weakness; Produce action document
‹

## Player
Player Usability Survey Questionnaires | Player Pre-Post Effectiveness Goals
1. What did you like most about the game? | Category | Goals
2. What did you found confusing? | Education | 50% of players can name three things to save electricity
3. What issues did you have while using the game? | Behavior Change | 50% of players did one thing that reduces their consumption
4. What was the thing you liked the least about the game? |  | 20% of players made at least 1 conservation commitment
5. What can we do to improve the game? | Resource Reduction | 3% of average reduction
6. It was easy to find what I was looking for on the website.
Strongly disagree - Disagree - Neutral - Agree - Strongly agree
7. The website was responsive. | Player Engagement Metrics Goals
Strongly disagree - Disagree - Neutral - Agree - Strongly agree | Metric | Definition | Goals
8. The website provided adequate help in teaching me how to play. | participation | percentage of players who participated in the game | 30%
Strongly disagree - Disagree - Neutral - Agree - Strongly agree | daily player | average percentage of players per day | 5%
9. I understood how to play. | daily play time | average play time of a player per day | 5 minutes
Strongly disagree - Disagree - Neutral - Agree - Strongly agree | submission | average submissions of a player | 2
10. this is something my friends should participate in. | social interaction | average social interaction of a player | 2
Strongly disagree - Disagree - Neutral - Agree - Strongly agree | game error | percentage of players who encountered errors | 1%

## System Admin
System admin Post-hoc Interview Questionnaires
1. How much time did you spend to install the system and the dependencies?
2. How much time did you spend to configure the meters?
3. How much time did you spend to maintain the system such as backup, patching, monitoring?
4. Did you need to scale the system? if Yes, how much time did you spend?
5. What problems did you encounter?
6. Did you find it difficult to admin the system? What was difficult?
7. Do you agree for us to call you for a short phone interview if we have more questions regarding your experience with the system?

## Game Designer
Game Designer Post-hoc Interview Questionnaires
1. How much time did you spend to set up the buildings including meters?
2. How much time did you spend to setup the competition (competition periods, baseline period, participants)?
3. How much time did you spend to setup the homepage by deciding which widgets to include?
4. How much time did you spend to monitor analytical data to understand the state of the game
5. What problems did you encounter?
6. Did you find it difficult to use the interface? What was difficult?
7. Do you agree for us to call you for a short phone interview if we have more questions regarding your experience with the system?

## Game Manager
Game Manager Post-hoc Interview Questionnaires
1. How much time did you spend to enter the meter data manually for the baseline period?
2. How much time did you spend to enter the meter data manually for the competition period?
3. What problems did you encounter?
4. How much time did you spend to monitor analytical data to understand the state of the game
5. Did you find it difficult to manage? What was difficult?

## Game Developer
Game Developer Post-hoc Interview Questionnaires
1. How much time did you spend to implement the creation of a new widget?
2. How much time did you spend to implement adding a new type of meter?
3. What problem(s) did you encounter?
4. Did you find it difficult to understand, extend and debug the system? What was difficult?